## Weekly Gantt Chart Template
AI (Deep Learning) Systems for Medical Image Analysis and Diagnosis
|  | Azam Muhammad Adeel |  | Dr. Leonardo De Mattos | [9 empty] | 2020-01-11 | [10 empty] | 30/10/2023
|  | NAME |  | Supervisor | [9 empty] | START DATE | [10 empty] | END DATE
Project Description | Task ID | Task Name | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
This project will develop AI technologies to automatic detect, diagnose and delineate LSCC on endoscopic videos. |  |  | Month | Month
| 01 | LSCC detection and Informative frame extraction | 1 | 12
| 01.01 | Define Objectives | 1 | 2
| 01.02 | Literature review | 3 | 4
| 01.03 | Dataset Collection | 5 | 6
| 01.04 | Informative frames results | 7 | 8
| 01.05 | LSCC detection results | 9 | 10
| 01.06 | Final remarks and Article Writup | 11 | 12
| 02 | AI system for real-time informative frame selection | 13 | 19
| 02.01 | Literatue review | 13 | 14
| 02.02 | Experiments usign AI models | 15 | 16
| 02.03 | Results and writeup | 17 | 19
| 03 | AI system for LSCC detection, segmentation and delineation | 20 | 31
Remarks | 03.01 | Literature review | 20 | 21
Monthly monitoring shall be done to check if the objectives are being achieved. Improvement on the action plans shall be enhance along the way. | 03.02 | Experiment on segmentation | 22 | 23
| 03.03 | Results of segmentation | 24 | 25
| 03.04 | Experiment on tumor delineation using AI | 26 | 27
|  | Results of tumor delineation | 28 | 29
|  | Article writeup | 30 | 31
| 04 | Systems integration and Thesis write-up | 32 | 36
| 04.01 | Task one results integeration | 32
| 04.02 | Task two results integeration | 33
| 04.03 | Task three results integeration | 34
| 04.04 | Final output AI system | 35
| 04.05 | Thesis writeup | 36

## Sheet2
Development of Endoscopic OCT for Vocal Cord
| Ajay Gunalan |  | Dr. Leonardo De Mattos | [9 empty] | 2020-01-11 | [10 empty] | 30/10/2023
| NAME |  | Supervisor | [9 empty] | START DATE | [10 empty] | END DATE
Task ID | Task Name | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  | Month | Month
01 | Problem Formulation & Literature Review | 1 | 6
02 | A Scan OCT | 6 | 12
03 | EndoOCT scanner | 13 | 19
04 | Tailored Sensing | 20 | 24
05 | OCT-guided laser surgery | 25 | 30
06 | Integration of endoOCT scanner | 31 | 36

## ©
© TemplateLab.com